## Gantt Chart
GANTT Chart Lockheed Martin #2
PROJECT TITLE |  | Digital Twin |  |  |  |  | COMPANY NAME | [6 empty] | Lockheed Martin
PROJECT CONTACT |  | Jonathan Klingel |  |  |  |  | COMPLETION DATE | [6 empty] | 2021-04-30
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [19 empty] | PHASE TWO | [19 empty] | PHASE THREE | [19 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | Weel 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | Week 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | Week 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | Week15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Modify Tb&S Solution
1.1 | Identify Strengths and Weaknesses of Tb&S Heat Model Analyzer |  | 2021-01-18 | 2021-01-22 | 4 | 0% | bar: WEEK 1 M to WEEK 1 F
1.2 | Improve existing Tb&S Heat Model Analyzer |  | 2021-01-21 | 2021-02-12 | 21 | 0% | bar: WEEK 1 R to WEEK 4 F
2 | Non-Tb&S Integration
2.1 | Integrate Non-Tb&S Heat Model Analysis |  | 2021-02-15 | 2021-03-12 | 27 | 0% | bar: WEEK 5 M to WEEK 8 F
3 | Translation Automation
3.1 | Automate Translation of I/O Between Thermal Models |  | 2021-03-15 | 2021-04-09 | 24 | 0% | bar: WEEK 9 M to WEEK 12 F
4 | Project Finalization
4.1 | Explore Generalization of Translation Tool |  | 2021-04-12 | 2021-04-21 | 9 | 0% | bar: WEEK 13 M to WEEK 14 W
4.2 | Provide Documentation for Finished Product |  | 2021-04-19 | 2021-04-30 | 11 | 0% | bar: WEEK 14 M to Week15 F
4.3 | Develop and Present Demonstration |  | 2021-04-19 | 2021-04-30 | 11 | 0% | bar: WEEK 14 M to Week15 F