## WBS
Lockheed Martin #2
Project Start |  | 2019-01-07
[42]
Level | WBS | Task Description | Assigned To | Start | End
1 | 1 | Improve Tb&S Model Analyser (Phase 1) |  |  | Mid Febuary
2 | 1.1 | Identify Strengths and Weaknesses and Tb&s model Analyser | Tb&S analyzer team | 2021-01-18 | 2021-01-22
3 | 1.1.1 | Meet with product owner | Tb&S analyzer team | 2021-01-18 | 2021-01-22
2 | 1.2 | Improve Tb&S model analyzer | Tb&S analyzer team | 2021-01-21 | 2021-02-12
3 | 1.2.1 | Implement Inprovements | Tb&S analyzer team | 2021-01-21 | 2021-02-12
1 | 2 | Non Tb&S Integration (Phase 2) |  |  | Due Mid March
2 | 2.1 | Understand Thermal Desktop | Non Tb&S team | 2021-02-15 | 2021-02-25
3 | 2.1.1 | Develop Plan | Non Tb&S team | 2021-02-26 | 2021-03-06
3 | 2.1.2 | Integrate | Non Tb&S team | 2021-03-07 | 2021-03-15
1 | 3 | Translation Automation (Phase 3) |  |  | Due Mid April
2 | 3.1 | Look at I/O of Tb&S | Translation Team | 2021-03-07 | 2021-03-16
3 | 3.1.1 | I/O Non Tb&S | Translation Team | 2021-03-15 | 2021-03-21
4 | 3.1.1.1 | Automate Translation of I/O Between Thermal Models | Translation Team | 2021-03-22 | 2021-04-15
1 | 4 | Project Finalization |  |  | Due End April
2 | 4.1 | Explore Generalization of Tool | CU Capstone Team | 2021-04-12 | 2021-04-21
2 | 4.2 | Provide Documentation for Finished Product | CU Capstone Team | 2021-04-19 | 2021-04-30
2 | 4.3 | Develop Demonstation | CU Capstone Team | 2021-04-19 | 2021-04-30
3 | 4.3.1 | Create Demonstration | CU Capstone Team | 2021-04-19 | 2021-04-30
3 | 4.3.2 | Present Demonstration | CU Capstone Team | 2021-04-30 | 2021-04-30
[6 empty] | Tb&S analyzer team | Jared | Karthik | Brandon | Owen
[6 empty] | Non Tb&S team | Matt | Brain | James
[6 empty] | Translation Team | Owen | Brandon | Matt
[6 empty] | CU Capstone | all members